# Fargo Expansion - Steering Workshop - Meeting Transcript

Date: 24 March 2027  |  Duration: 09:00 - 12:30  |  Location: Contoso Fargo, Conference Room 2

Participants: Sydney Mattos (chair, regional operations), Teresa Sac (logistics Fargo), Vance DeLeon (construction), Sonia Rees (safety and training), Billie Vester (IT).

Sydney: Good morning. We have three and a half hours to settle the plan for the new wing. I want clear decisions today, and I want to know what is still open when we leave. Teresa, start with the carriers.

Teresa: Dock 3 closes on April 27. From then on we lose two inbound doors for about eight weeks. Fabrikam can use Gate 4 from April 30. For the three days in between they need a slot at Dock 2, seven to nine in the morning.

Sydney: Can we do that at Dock 2?

Vance: Yes, Dock 2 is free in that window. No construction traffic there.

Sydney: Good. Decision: Fabrikam gets the Dock 2 slot from April 27 to April 29 and uses Gate 4 from April 30. Anyone against?

Sonia: No, that works.

Teresa: Next point. Should we move the Dock 3 closure by two weeks? Some of us wanted more time for the carriers.

Vance: I would not. The cable trays are already ordered for the closure date. Moving it by two weeks pushes electrical to the end of June and kills go-live.

Sydney: Then we keep April 27. The trade-off is eight weeks with fewer doors against a go-live that stays on June 22. Decision made.

Teresa: Northwind arrives at 5:30 in the morning. The vendor window starts at 6:00. If they move to 6:15 they lose their slot in Minneapolis.

Sonia: I cannot sign off on trucks on site before the window without supervision. The lighting at Gate 4 is not good enough before 6.

Vance: We could put up temporary floodlights. Two units, rented, about two thousand dollars for the month.

Sonia: With floodlights and one marshal, I could accept a trial. Not an open-ended exception.

Sydney: Then: a four-week trial from April 30, Northwind may arrive from 5:30 with floodlights and a marshal. Sonia reviews it on May 28 and decides whether it continues.

Sonia: Agreed. I will review on May 28.

Teresa: Saturday shifts for wave 1 are approved for May 2 and May 9. The problem is May 9. I still need four forklift drivers.

Sydney: Where do we get them?

Teresa: Either temp agency or from the Minneapolis site. I do not know yet which is cheaper.

Sydney: Okay, that stays open. We cannot decide without numbers. Teresa, get quotes.

Teresa: I can try. I do not have a date for it yet.

Sydney: Let's leave the date out for now.

Teresa: Wave 1 is the A items only. Looking at the data from the last quarter, I think we should add the B items. Otherwise wave 2 is overloaded.

Sydney: Then wave 1 covers A and B items. Everyone fine?

Vance: Fine for construction.

Sonia: Safety is fine as long as the mezzanine is not part of wave 1.

Sydney: The mezzanine stays out of wave 1. Decision: wave 1 is A and B items, no mezzanine.

Sydney: One idea: we could run extra Sunday shifts to catch up. Teresa?

Teresa: Possible in principle.

Sonia: Careful, our labor agreement limits Sunday work. Without the works council that does not work.

Sydney: Right. Scrap the Sunday idea, it was only a thought. Do not minute it as a decision.

Vance: Update from the building site. Electrical in the new wing will be finished on May 22, not May 15. That uses up a week of the buffer. Go-live on June 22 is still possible.

Sydney: Is there anything that would make you say June 22 is not safe?

Vance: If the sprinkler test slips beyond June 1. At the moment the inspector has not confirmed a date.

Sonia: I would be uneasy if the test is not done two weeks before go-live.

Sydney: Then we need a go/no-go point. Decision: go/no-go for June 22 on June 8, chaired by me. Vance brings the sprinkler test result.

Vance: I will ask the inspector again this week. I cannot promise a date from him.

Billie: IT point: the scanners in the new wing. The Wi-Fi survey can only be done when the electrical work is complete, so not before May 22.

Sydney: When do the scanners go live then?

Billie: June 1 is realistic. May 15 is not possible any more.

Sydney: Decision: scanner go-live in the new wing moves from May 15 to June 1.

Billie: I need the Wi-Fi survey as a task, though. I am not sure who owns it. Could be facilities.

Vance: Not us, we only deliver the cabling.

Sydney: Open then: who runs the Wi-Fi survey, and when. We need an owner next week.

Teresa: Temporary staff for the peak after go-live: how much budget do we have?

Sydney: I would like to hold at 120 thousand dollars. But finance has not confirmed. Treat it as an open item, I will clarify.

Teresa: Tailspin Toys is asking about the Dock 3 closure. Someone should tell them what changes for deliveries.

Sydney: Yes. Who does it and when, we should settle that. Let's note it as open.

Sonia: Safety training for the new wing: all forklift drivers need the new traffic rules before May 31. I will schedule sessions in the week of May 17.

Sydney: Good: Sonia runs the safety training in the week of May 17, all drivers complete by May 31.

Sydney: Let me summarize what I heard. I will send a note. Thanks everyone.