## Slide 1
Fargo expansion: where we stand
Operations update · Week 14

## Slide 2
We are on track for go-live on Jun 22
24
weeks
total project plan
14
of 24
weeks completed
1
week
possible delay (electrical)

## Slide 3
Dock 3 closes on Apr 27 – inbound moves to Dock 2
All inbound trucks use Gate 4 and Dock 2 from Apr 27.
Carriers are informed; two still need confirmation (Lisa).
Extra Saturday shifts at Dock 2 for wave 1 (A items).
Yellow forklift floor markings in Hall 2 ordered (Kai).

## Slide 4
East corridor escape route is closed
Detour via mezzanine A and the north stairs.
New assembly point: C.
PPE required in all zones next to the construction site.
Updated evacuation maps go up in every hall this week (Sonia).
Not all new maps are up yet

## Slide 5
Next steps
What | Who | By
Confirm remaining carriers for Dock 2 | Lisa | Apr 20
Approve sprinkler test | Facility + insurer | Apr 10
Train shift leads on new safety rules | Sonia | Apr 24
Floor markings Hall 2 | Kai | Apr 17