## Fargo dock schedule
Date | Start | End | Dock | Gate | Carrier | Type | Load | Notes | Owner | Status
2027-04-27 | 06:30 | 08:30 | Dock 2 | Gate 4 | Fabrikam Logistics | Inbound | Pallet racks | Transition slot while Dock 3 closes | Lisa Taylor | Confirmed
2027-04-28 | 07:00 | 09:00 | Dock 2 | Gate 4 | Fabrikam Logistics | Inbound | Packaging supplies | Use Gate 4 detour signage | Lisa Taylor | Confirmed
2027-04-29 | 05:30 | 06:15 | Dock 2 | Gate 4 | Northwind | Inbound | Line-side totes | Safety exception requested; early arrival before vendor window | Sonia Rees | Exception pending
2027-04-29 | 07:15 | 08:30 | Dock 2 | Gate 4 | Fabrikam Logistics | Inbound | Conveyor spares | Northwind must clear Gate 4 first | Lisa Taylor | Confirmed
2027-04-30 | 08:00 | 10:00 | Dock 2 | Gate 4 | Fabrikam Logistics | Inbound | A-item cartons | Gate 4 standard route starts | Lisa Taylor | Confirmed
2027-05-02 | 09:00 | 12:00 | Dock 2 | Gate 4 | Northwind | Outbound | Tailspin Toys partial shipment | Hold until sprinkler sign-off is recorded | Lisa Taylor | Tentative
2027-05-09 | 07:00 | 13:00 | Dock 2 | Gate 4 | Internal move | Inventory | Wave 1 A-items | Needs four more forklift drivers | Lisa Taylor | At risk
2027-06-15 | 10:00 | 11:30 | New wing | East Corridor B | Contoso | Safety | Evacuation drill | Must complete before go/no-go | Sonia Rees | Planned
2027-06-22 | 06:00 | 14:00 | Dock 2 | Gate 4 | All carriers | Go-live | New wing cutover | Use new safety routes | Ops lead | Planned