# Construction weekly – week 16 – Fargo expansion

Attending: Sonia (Safety), Kai (Construction), Lisa (Logistics), operations lead

## Decisions

Dock 3 closes as planned on April 27. Inbound moves to Dock 2 and Gate 4.

Go-live of the new wing stays on June 22. Go/no-go decision on June 15, after the evacuation drill.

Saturday shifts for wave 1 approved for May 2 and May 9.

## Open points

Electrical is one week late (May 22 instead of May 15). Kai sends a revised plan.

Sprinkler test moved to April 20. Approval from Facility and insurance still missing. Owner unclear.

Northwind Freight arrives at 5:30 am, before the vendor window. Safety exception needed (Sonia).

Shift lead training: 12 people, dates in the week of June 7 still to be set.

Key customers have not been told about the reduced dock capacity yet (operations lead).

## Next meeting

Thursday, 10:00 am, Dock 1 meeting room and Teams.