## Readiness
ID | Workstream | Item | Owner | Due | Status | RAG | Notes
R01 | Logistics | Move inbound to Dock 2 / Gate 4 | Lisa | 2027-04-27 | In progress | Amber | Northwind 5:30 am exception still open
R02 | Logistics | Carrier confirmations (Northwind, Fabrikam Logistics) | Lisa | 2027-04-24 | In progress | Amber | Fabrikam Gate 4 from Apr 30; needs Dock 2 slot Apr 27–29
R03 | Logistics | Saturday shifts wave 1 | Lisa | 2027-05-02 | Open | Amber | 4 forklift drivers missing for May 9
R04 | Construction | Electrical new wing | Kai | 2027-05-15 | In progress | Red | Cable trays late, new date May 22
R05 | Construction | Floor markings Gate 4 | Kai | 2027-04-25 | Open | Amber | Gate 4 closed Apr 24–25
R06 | Construction | Sprinkler test new wing | Kai | 2027-04-13 | Open | Red | Facility + insurance approval missing
R07 | Safety | Detour signage east corridor escape route | Sonia | 2027-04-10 | Done | Green
R08 | Safety | Shift lead training new safety rules | Sonia | 2027-06-12 | Open | Amber | 12 shift leads, dates tbd
R09 | Safety | Evacuation drill new wing | Sonia | 2027-06-15 | Open | Green
R10 | Inventory | Wave 1 move (A items) | Lisa | 2027-05-09 | Open | Amber | Depends on Saturday shifts
R11 | Inventory | Wave 2 move (B/C items) | Lisa | 2027-06-05 | Open | Green
R12 | IT | Scanners and Wi-Fi new wing | Alex | 2027-06-01 | Open | Green | Needs electrical done
R13 | Customers | Inform key customers about reduced dock capacity | Ops lead | 2027-04-20 | Open | Amber
R14 | Go-live | Go/no-go decision | Ops lead | 2027-06-15 | Open | Green | After evacuation drill

## Milestones
Milestone | Date
Sprinkler test | 2027-04-13
Dock 3 closes, inbound via Dock 2 / Gate 4 | 2027-04-27
Wave 1 inventory move done | 2027-05-09
Electrical new wing done | 2027-05-15
Evacuation drill | 2027-06-15
Go/no-go decision | 2027-06-15
Go-live new wing | 2027-06-22