# Contoso Fargo Distribution Center Expansion – Project Overview

This document provides a high-level overview of Contoso’s distribution center expansion in Fargo. It summarizes project goals, key milestones, affected areas, construction phases, operational impacts, and critical dates throughout the project.

## Project Summary

Contoso is expanding its regional distribution center in Fargo to support increased product volume, improve shipping efficiency, and modernize facility operations. The project adds a new warehouse wing, upgrades critical infrastructure, and introduces new safety and logistics processes that will improve overall operations.

## Key Dates & Milestones (24-Week Timeline)

• Project Kickoff: January 05, 2026

• Site Preparation Begins: January 12, 2026

• Foundation Work Complete: February 02, 2026

• Building Framing Complete: March 02, 2026

• Electrical & Systems Installation: March 30, 2026

• Sprinkler System Installation & Testing: April 13, 2026

• Loading Dock 3 Upgrade: April 27, 2026

• Internal Facility Systems Integration: May 11, 2026

• Final Structural & Safety Inspection: June 08, 2026

• Go-Live Readiness Review: June 15, 2026

• Official Go-Live: June 22, 2026

## Affected Areas

• New warehouse wing construction zone
• Loading Dock 3 (closed during upgrades and testing)
• Temporary forklift routing paths
• Adjusted evacuation routes during construction
• Vendor and contractor access points

## Operational Impacts

• Temporary rerouting of inbound and outbound freight
• Adjusted floor traffic patterns and staging zones
• Expanded PPE requirements in work-adjacent areas
• Inventory moves occurring in phased waves across the project
• Increased coordination across Logistics, Safety, Operations, and Facilities

## Construction Phases

1. Site Preparation – clearing, marking utilities, excavation
2. Foundation Work – pouring base, installing supports
3. Structural Framing – wall, roof, and exterior framing
4. Electrical & Systems – lighting, power, HVAC, conveyor sensors
5. Fire & Life Safety – sprinklers, alarms, safety testing
6. Loading Dock Upgrades – door systems, leveling gear, railings
7. Facility Systems Integration – IT, RFID, automation components
8. Final Inspection – safety, compliance, and structural checks
9. Go-Live Preparation – cleaning, equipment setup, signage, training

## Safety Considerations

• PPE required in designated construction zones (hard hat, vest, gloves)
• Temporary evacuation routes clearly marked throughout the facility
• Restricted access for unauthorized personnel
• Vendor escorts required in active construction areas