# Contoso Fargo go-live source pack

Scenario: New warehouse wing in Fargo. Dock 3 closes on Apr 27; inbound moves to Dock 2 / Gate 4. Go/no-go Jun 15, go-live Jun 22.

# Construction weekly – week 16

| Workstream | Item | Date | Owner | Note |
| --- | --- | --- | --- | --- |
| Construction | Electrical | May 22 | Kai | Late cable trays; buffer reduced to one week. |
| Construction | Sprinkler test | Apr 20 | Kai | Facility and insurance approval still missing. |
| Logistics | Gate 4 markings | Apr 24-25 | Lisa | Gate closed while floor markings are applied. |
| Safety | Shift lead training | Week of Jun 7 | Sonia | Three 90-minute sessions, four leads each. |
| IT | Scanner / Wi-Fi test | Jun 1 | Alex | Depends on electrical completion. |

# Email snippets

## Dock 3 cutover: carrier plan for Apr 27

From: Lisa Taylor

Dock 3 closes after Friday Apr 26. Northwind keeps the 5:30 am inbound slot, Fabrikam Logistics needs 7-9 am coverage at Dock 2 for Apr 27-29, and Gate 4 opens for Fabrikam from Apr 30. I am worried about Dock 2 on Mondays once Dock 3 traffic moves over.

## New wing construction update

From: Kai Carter

Electrical completion moves to May 22. Sprinkler test is now Apr 20 and still needs Facility and insurance sign-off. Gate 4 floor markings are Apr 24-25, so do not schedule inbound there then.

## Safety prep before go-live

From: Sonia Rees

All 12 shift leads need training in the week of Jun 7. Evacuation drill for the new wing is planned for Jun 15, before the go/no-go meeting.

## Scanner and Wi-Fi readiness

From: Alex Weyer

Wi-Fi install depends on electrical completion. If electrical holds at May 22, scanner testing can start Jun 1 and still finish before go/no-go.

# Runbook draft notes

Purpose: coordinate the Dock 3 closure, new wing readiness and go-live decision.

Audience: Logistics, Construction, Safety, IT and Operations leads.

The runbook should be concise, action-oriented and written for a live operations call.

Include a RACI table and a short daily rhythm from Apr 24 through Jun 22.