Dock 3 go-live sync

Teams meeting recap and transcript · Contoso Fargo · Apr 24, 2027

# Meeting recap

| Type | Note |
| --- | --- |
| Decision | Inbound moves from Dock 3 to Dock 2 on Apr 27. Gate 4 is the preferred staging area after floor markings finish. |
| Risk | Fabrikam Logistics can use Gate 4 from Apr 30, but Apr 27–29 need a temporary Dock 2 slot from 7:00–9:00. |
| Risk | Northwind Freight still arrives at 5:30, outside the 6:00–20:00 vendor window. Safety exception needed. |
| Dependency | Sprinkler test moved to Apr 20; Facility and insurance approval still open. |
| Dependency | Electrical completion moved to May 22. Wi-Fi and scanner setup cannot finish before electrical is signed off. |
| Action | Sonia to confirm evacuation drill timing for Jun 15 before the go/no-go meeting. |
| Action | Teresa to confirm four forklift drivers for the May 9 Saturday shift. |
| Action | Ops lead to prepare a night-shift handover page by Apr 26. |

# Transcript excerpt

Teresa Sac: The main thing for logistics is that Dock 3 is effectively out from Monday morning. Fabrikam can switch to Gate 4 on Apr 30, but the first three days are tight.

Vance DeLeon: Gate 4 markings happen Apr 24 and 25. Please do not route carriers there until I confirm the paint is cured and the cones are removed.

Sonia Rees: Northwind at 5:30 is before the approved vendor window. I can support an exception, but I need the new Dock 2 marshal plan attached.

Billie Vester: Scanner setup depends on electrical sign-off. If May 22 slips, Wi-Fi in the new wing becomes a red risk.

Ops Lead: I'll put all of this in the Fargo notebook and create a night-shift handover so supervisors can run the same checklist.